## Sheet1
IPTV CHANNEL HIGH LEVEL TIMELINE
[44 empty] | RESOURCES | $ | Notes | time axis 2013-02-04 to 2013-11-25
PROJECTS
WORKS.TV
Business requirements spec | 2013-02-04: COMPLETE
UX | [43 empty] | Katja | 25000 | COMPLETE | bar: 2013-02-04 to 2013-02-11
Visual Design | [43 empty] | Chris |  | 90% | bar: 2013-02-18 to 2013-02-25
PHASE 1 - Development (desktop) | [43 empty] | Robbie | bar: 2013-03-04 to 2013-04-29
PHASE 1 - Development (mobile) | [43 empty] | Robbie | bar: 2013-03-04 to 2013-03-25; 2013-05-06 to 2013-05-20
LAUNCH WORKS.TV PHASE 1 | bar: 2013-03-04 to 2013-03-25; 2013-05-20
PHASE 2 - Development (desktop) | [43 empty] | Robbie | bar: 2013-03-04 to 2013-03-25; 2013-05-27 to 2013-06-10
PHASE 2 - Development (mobile) | [43 empty] | Robbie | bar: 2013-03-04 to 2013-03-25; 2013-06-17 to 2013-07-01
LAUNCH WORKS.TV PHASE 2 | bar: 2013-03-04 to 2013-03-25; 2013-07-01
ChannelPLAY (4ME)
Business requirements spec | [43 empty] | DB |  | COMPLETE
UX | [43 empty] | Katja | $13,000 - $20,000 | COMPLETE | bar: 2013-02-04 to 2013-02-18
Visual Design | [43 empty] | Chris | bar: 2013-02-25 to 2013-03-18; 2013-04-01 to 2013-04-15
Development | [43 empty] | Simon/Iz | bar: 2013-03-18 to 2013-03-25; 2013-04-22 to 2013-06-24
LAUNCH 4ME SG | bar: 2013-06-24
Development 4ME AU | [45 empty] | Taking linear feed from existing Sydney playout provider for the ON NOW feature | bar: 2013-06-24 to 2013-07-29
LAUNCH 4ME AU (including eCommerce) | bar: 2013-03-04 to 2013-03-25; 2013-07-29
Smart TV App | [43 empty] | TBC | $50-$60,000 | To be confirmed | bar: 2013-06-03 to 2013-10-28
iSurf
Business requirements spec | [43 empty] | Stu | bar: 2013-04-01
Visual Design | [43 empty] | Chris | bar: 2013-05-06 to 2013-05-20
Development (front end) | [43 empty] | Dev - TBC | bar: 2013-05-27 to 2013-06-10
Development (backend) | [43 empty] | Dev - TBC | bar: 2013-06-17 to 2013-07-01
LAUNCH | bar: 2013-07-01
Project Manager | [43 empty] | TBC |  | 50% allocation | bar: 2013-04-01 to 2013-07-01
Surfing Competition Site | bar: 2013-04-01 to 2013-04-15
Visual Design | [43 empty] | Chris | bar: 2013-04-01 to 2013-04-15; 2013-06-10 to 2013-06-24
Development (front end) | [43 empty] | Dev - TBC | bar: 2013-04-01 to 2013-04-15; 2013-07-01 to 2013-07-15
Development (backend) | [43 empty] | Dev - TBC | bar: 2013-04-01 to 2013-04-15; 2013-07-22 to 2013-08-05
LAUNCH | bar: 2013-08-05
food4life (ChannelPLAY clone)
Business requirements spec | [43 empty] | DB
UX | [43 empty] | Katja | 5000
Visual Design | [43 empty] | Chris | bar: 2013-07-08 to 2013-07-22
Development | [43 empty] | Dev - TBC | bar: 2013-07-29 to 2013-08-26
LAUNCH | bar: 2013-08-26
OTHER
healthyMEtv (ChannelPLAY clone)
Business requirements spec | [43 empty] | DB
UX | [43 empty] | Katja | 5000
Visual Design | [43 empty] | Chris | bar: 2013-06-17 to 2013-06-24
Development | [43 empty] | Dev - TBC | bar: 2013-07-01 to 2013-07-15
RE-Launch | bar: 2013-07-15
homecook.tv
Business requirements spec
UX
Visual Design
Development